**Reallocation Timeline for HUD Rapid Rehousing Project**

**August 1**-Release of opportunity to assume grant reallocation with application.  Request for Allocation and Accountability Committee members to Mark by **August 19**.

**August 19** -Applications Due to Christina Fort.

**August 21**-Send out applications and scoring tool to AAC.

**August 28**- Scoring rubrics due to Mark. Scores tabulated.

*\*Zoom meeting to reach consensus on selection, if needed:* ***Sept 4th***

*Will need a few days to obtain vote from Exec Committee following recommendation from AAC*

**September 9**   -Announce reallocation award to agency.  Announce to LHA.